## Group Log
Essential links
Trello
GDrive
Jitsi
Github
Aside from these big meetings: we also do daily stand-ups, for max 20 mins after class on weekdays, and one on Sunday at 1O AM BST for an hour
Date | Time (BST) | Agenda | Minutes | Remarks
27/04/2023 | 8:30 - 9:15 PM | Decide on a project | Meeting 1
30/04/2023 | 10:00 - 11:00 AM | Task Division | Meeting 2
2023-01-05 | 6:00-7:00PM | Consultaton with Anuj | Meeting 3
2023-04-05 | 8:00 - 9:00 | Consultaton with Anifah | Meeting 4
2023-10-05 | 8:30 - 11:30 PM | Homework 2 | Homework 2
20/05/2023 | 2PM - 2:40PM | Kathleen and Mungu meeting on Front End
20/05/2023 | 10PM - 10:40PM | Kathleen and Nia meeting about linking Python to SQL
28/05/2023 | 10:30pm-11:45pm | Final team meeting to discuss final touches before submitting project

## Munguu
Mungunzaya Ganbat
Date | Activity/Task | Time spent on Activity: | COMPLETED? | Links used | Notes
SPRINT 1: WEEK 1
31/04/23 | Created design/architecture diagram | 30mins | YES | Python client library for Google Maps API Web Services
| Extended main considerations of the project | 30mins | YES | geopy · PyPI
| Created process flow table from user perspective + application logic | 1 hour | YES | GeoIP and GeoLite ¦ MaxMind Developer Portal
Geolocate an IP address using Web Services ¦ MaxMind Developer Portal
Draw.io for drawing the diagram: diagrams.net
2023-05-01 | Summarizing key requirements, creating design diagram on Draw.io | 2 hour | YES
2023-05-02 | wrote the worker functions for the login page | 2 hour | YES
2023-05-03 | Created draft code for login, profile creation and location page using streamlit | 1 hour | YES
2023-05-04 | Created SQL connection to login page | 4 hour | YES
2023-05-05 | Decided not to use location page as a team, so removed it | 15mins | YES
2023-05-06 | CREATED LOGIN, SIGNUP, PROFILE CREATION PAGES | 2 hours | YES
2023-05-07 | FIXED APP.PY to get the other functions running | 1 hour | YES
2023-05-08 | FIXED SQL, DB connection to insert data into users table for saving users information | 2 hours | YES
2023-05-09 | Added more functionality to the HTML part via creating sidebar menu with options for delete_my_account, logout, favourites, login and security pages | 4 hours | YES
2023-05-10 | Wrote the functions and tested the functionality for the delete_my_account, logout, login and security pages |  | YES
2023-05-11 | Participated in writing Homework 2 | 1 hour 30mins | YES
2023-05-12 | Debugged the existing codes | 3 hours | YES
2023-05-13 | on a flight to Mongolia | - | YES
2023-05-14 | on a flight to Mongolia | - | YES
2023-05-15 | Refactored the existingcodes into OOP class with SOLID principles | 4 hours | YES
2023-05-16 | Added exception handling and user authentication using regex function to login_signup_page, | 3 hours | YES
2023-05-17 | signup and login has been separated, so it can reused easily in other functions | 1 hour | YES
2023-05-18 | Wrote unit testing for Login_signup_page | 1 hour 15mins | YES
2023-05-19 | Wrote unit testing for Login_security_page | 1 hour | YES
2023-05-20 | Fixed login_signup_page as i am having functionality error for duplicate widget error: Refactoring the login_signup page by creating an instance of UserAuthenticator class in the function, and refactored the a single big function into 4 smaller functions with each having a single responsibility (show_login(), show_signup(), get_signup_login_choice(), login_signup_choice()) | 2 hour | YES
2023-05-21 | Fixed User class authenticator: User Authenticator Class where the user details (username, password, email) are validated using regex, and checking email and username exists. Furthermore, with the use of Exception Handling, raising errors for invalid formats for username, password, and email became possible, and also successfully added the function (get_user_info()) for returning the user details that were used for different pages to connect the front-end to back-end | 1 hour 30 mins | YES
2023-05-22 | Learning about how to use mock and patch, fixed SQL connection error in security (login and Security), Took part in handling DuplicateWidgetID error issues alongside Kathleen that were happening in login_signup page for st.selectbox widgets with the same generated key by trying out different ideas (e.g. using random library to generate unique key for every widget by assigning the key variable in the st.selectbox, using st.radio instead of st.selectbox etc), however, my solutions didn’t solve the initial problem. | 2hour | YES
2023-05-23 | Learning about how to use mock and patch to write unittests, and project documentation | 4hour | YES
2023-05-24 | Fixed delete_account (did debugging, refactored the whole code for readability), project documentation: Wrote the sql_connection.py with exception handling in a single function for suitable sql connection, Before it was defined to ‘mydb’ variable, which worked fine, however while doing unit-testing for the front-end pages,it was deemed to be better to wrap the connection inside a function instead of a variable. | 2hour | YES
2023-05-25 | Fixed Login and Security (did debugging, found the error that was causing it and fixed it): Login and Security functionality where user can decide to change either of the following (username,password, and email), and also successfully connected the front-end to the SQL by fetching data, comparing if it already exists and updating the SQL table users with the new user_input (Munguu). | 3hour 30mins | YES
2023-05-26 | Wrote unittest for security, send_email, user_authenticator | 4hour | YES
2023-05-27 | Wrote unittest for delete_account, food_preferences, login_signup, project documentation | 3hour | YES
2023-05-28 | Project Documentation | 5hour | YES
User Authenticator Class where the user details (username, password, email) are validated using regex, and checking email and username exists. Furthermore, with the use of Exception Handling, raising errors for invalid formats for username, password, and email became possible, and also successfully added the function (get_user_info()) for returning the user details that were used for different pages to connect the front-end to back-end
Login and Security functionality where user can decide to change either of the following (username,password, and email), and also successfully connected the front-end to the SQL by fetching data, comparing if it already exists and updating the SQL table users with the new user_input (Munguu).
Refactoring the login_signup page by creating an instance of UserAuthenticator class in the function, and refactored the a single big function into 4 smaller functions with each having a single responsibility (show_login(), show_signup(), get_signup_login_choice(), login_signup_choice())
Took part in handling DuplicateWidgetID error issues alongside Kathleen that were happening in login_signup page for st.selectbox widgets with the same generated key by trying out different ideas (e.g. using random library to generate unique key for every widget by assigning the key variable in the st.selectbox, using st.radio instead of st.selectbox etc), however, my solutions didn’t solve the initial problem.
Wrote the sql_connection.py with exception handling in a single function for suitable sql connection, Before it was defined to ‘mydb’ variable, which worked fine, however while doing unit-testing for the front-end pages,it was deemed to be better to wrap the connection inside a function instead of a variable.

## Kathleen
Kathleen Kay Amora
Date | Activity/Task | Time spent on Activity: | Completed? | Libraries Used | Links used | Comments
SPRINT 1: WEEK 1
30.04.2023 | Created Project Diary | 30 mins | YES |  | Project Diary
| Created Github |  | YES |  | Github
| Added everyone as collaborators |  | YES
| Update Minutes |  | YES |  | Minutes of the Meeting
| Check out APIs: Zomato, Yelp Fusion API, use YELP | 2 hours | YES |  | Yelp Fusion API documentation | We have to change the expectations in our database, because the YELP Fusion API has no other settings such as Atmosphere/Menu
| Registered in Yelp Developers Hub to get private Authorization Key |  | YES |  | Guide to Yelp API | Easy to obtain private API key, just took time for me to create code to get data from API
| Created code to get info and view in browser using Flask |  | YES | requests, Flask | Yelp API | Retrieved categories: Name, Address, Rating, Price Range, Phone Number, Review Count, Kinds of Supported Transactions, Operating Hours (mostly N/A), Cuisine type, Location (Coordinates)
| Uploaded files (code, API key and .json files) in GitHub under Python folder |  | YES |  | Github link
01.05.2023 | Added geolocation | 1 hour | YES |  | https://geolocation-db.com/json' | All are in github project, sprint1 branch, python folder
| Added radius = 1000 (10 km) |  | YES |  |  | Seems like to work but with continuous runs, my Pycharm looked buggy
| Add menu |  | YES (but feature should be scrapped) |  |  | There is, but most of the restaurants that have this category shows empty results, not yet uploaded on Github
| Look for alternative geolocation APIs |  | YES |  | Some links to try: IPGeolocation: https://ipgeolocation.io/, GeoIPFY: https://geo.ipify.org/, Google Web App services: https://github.com/googlemaps/google-maps-services-python | Other Geolocation APIs are not for free, some also only have limted tokens so we have to be careful in using them.
| Convert json to csv |  | YES |  |  | Not yet uploaded to github
| Have to clean the file due to encoding issues |  | NO
02.05.2023 | Geolocation | 1 hour | NO
| Asked help to Fed about geolocation issues |  | YES |  |  | Having troubles with Flask caching in my computer!!!
04.05.2023 | Fix geolocation | 2 hours | NO
| Transfer Flask to Streamlit |  | YES
| Fix search criteria (shows up results staisfying Rating AND Cuisine) |  | YES
05.05.2023 | Tweaking code to add favorite button | 2 hours | YES
| Fix Save problem |  | NO
| Add function add_data_to_db |  | YES
| Test in streamlit |  | YES
| Figure out pages in Streamlit |  | YES
| Linking calling of functions and their dependencies across different files |  | NO
7.05 | Fixing save problem | 1 hour | NO |  |  | Created saving to csv (FOR NOW) both write (if not existing),or append (if existing) to check if results are fetched to csv. Also troubleshooted, calling the function WITHOUT the button press, WORKS, so technically function is OK!
| Studying st.session_state |  | YES
| Refactoring codes (created new functions) |  | YES
8.05 | Fix favorites button to st_multiselect | 4 hours | YES | OS, csv | Multiselect | Uploaded o github under python --> working_API_favorites
| Fix saving to csv (for now) |  | YES
| Study Python to SQL DB | 30 mins | NO
9.05 | Help Nia with SQL connection | 20 mins | YES |  |  | Uploaded to sql/python_db_connection.py
10.05 | Worked on Homework 2 | 2 hours | YES
11.05 | Refactoring codes from Fed | 30 mins | YES
15.05 | Review streamlit for codes for review and rating | 30 mins | YES
16.05 | Added review and rating code | 1 hr | YES
| Save comment and rating in CSV |  | YES
| Writing descriptions per function | 15 mins | YES
17.05 | Study mock in unit testing | 30 mins | YES
| Write unit-testing for some functions | 30 mins | YES
| Reorganized to classes (YelpAPI class) | 30 mins | YES
| Refactored some codes (created run function, fixed cuisine printing) | 20 mins | YES
20.05 | Unit Testing YelpAPI class (valid and invalid connection) | 1.5 hours | YES
| Tweaked add_data_to_db and save_review_rating_to_db to connect to SQL; took over the task from Nia as she expressed the need for help | 2.5 hours | YES | pymysql | pymysql package
| Meeting with Mungu to discuss the user_profile part she needed help on | 40 mins | YES
| Separated the saving functionalities to DB to a new class RestaurantToDB | 15 mins | YES
| Error handling/Exception handling | 30 mins | YES
| Meeting with Nia to explain the new SQL coding line by line | 40 mins | YES
| Working on front end error from codes of Munguu | 2 hours | NO |  |  | Recreated SQL tables, updated Mungu about the errors in the User Authentication and suggested to remove the st.radio part to avoid DuplicateWidgetID error
21.05 | Debugging front-end codes from Munguu | 1.5 hours | YES |  |  | Trial and error mode, googled other ways to create sign-up/log in using independent pages
22.05 | Started Project Documentation Introduction part | 1 hour | YES
| Helped Nia debug her own recreation of my SQL code | 1 hour | YES
| Coded in Python linking of restaurant_id (PK) from restaurants table as restaurant_ID (FK) in reviews table | 1.5 hour | YES
23.05 | Fixed Restaurant API layout | 30 mins | YES
| Project Documentation | 3 hours | YES
| Helped Nia with SQL | 40 mins | YES
24.05 | Contact Us page + Code + Set up Dummy CFGProject email | 1 hour | YES | smtp, ssl
| Work on Login issues with DuplicateWidgetID error (Mungu's problem) | 4 hours | YES |  |  | Finally fixed the core problem in user profile area, thus Mungu can now do her unit-test
25.05 | Integrating User Profile (Streamlit) ---> API ---> SQL |  | YES (but some issues still need to fix) |  |  | Still have session_state errors but mostly now working!!!!! It's like 80% done!
| Get data from SQL and publishing to Streamlit; adding functions |  | YES |  |  | By doing this, the whole core functionality of our app is complete
| Linking user_id to all SQL tables | 4 hours | YES
| Fix import of username across different pages |  | YES
| Figure out buggy favorites part, reverted one commit before Fed's update |  | YES
| Manage duplicate protection on restaurant tables when USER_ID is the same |  | YES
| Integrating User Profile (Streamlit) ---> API ---> SQL |  | YES (all issues somewhat fixed)
| Refactored RestaurantToDB function to avoid redundancy |  | YES
| Created create_connection function to house calling of credentials |  | YES
27.05 | Did another integration test, debugged issues on favorites due to overwrite in git | 3 hours | YES
| Fix unit-testing for API |  | YES
| Added check box in delete_account.py, revised Home |  | YES
| Project Documentation |  | YES
28.05 | Wrote 80% of the project documentaiton | 3 hours | YES
29.05 | Debugged unittest | 3 hours | YES
| Integrated testing | 3 hours | YES
| Upload files | 3 hours | YES

## Nia
Date | Activity/Task | Time spent on Activity: | Completed? | Libraries Used | Links used | Comments
31/04/2023 | Created the database and the tables in my SQL | 20 mins | YES |  |  | Waiting for the data from API to insert into the tables
2023-01-05 | Joined the tables in SQL database with relationships together | 20 mins | YES
2023-02-05 | Inserted the data from the API created by Kathleen | 40 mins | YES |  | Yelp API | Inserted the data manually line by line. Trying to think of better way to insert the data, instead of writing a query for each row
2023-04-05 | Call with Anifah to discuss the project and our ideas/progress so far | 30 mins | YES |  | Zoom
2023-04-05 | After meeting with Anifah we decided we do not need to insert all of the data for the restaurants to the table, decided to only save the users favourites. Discussed changes to the SQL tables to suit | 30 mins | YES
2023-05-05 | Made necessary changes to the database, and deleted tables and columns that were discussed with group | 30 mins | YES |  |  | Next step to connect the database to python and API, figuring out how to do that. Seem to think it will be best to connect the database to python first, then once that is connected successfullly, work on connecting to the Yelp API
2023-07-05 | Connecting SQL database to Python | 45 mins | NO | mysql.connector |  | No progress made. Encountering errors trying to make the connection form SQL, struggling to remember password and username for SQL to use in config file to make the connection. Trying to make a new connection. No successes
2023-09-05 | Connecting SQL database to Python | 30 mins | YES | mysql.connector |  | Connection made successfully. Figured out the error. Needed to usecursor.fetchall() after each query to connect to each table in the database as at first code would only run with one query. Next steps, connecting to API.
2023-10-05 | Homework week 2 | 1 hour 30 miins | YES |  |  | Completed homework week 2 as a group
12/05/2023 - 15/05/2023 | Away on holiday | N/A |  |  |  | No work completed (discussed with group at beginning of project
16/05/2023 | Researching how to make the API to db connection | 2 hours | YES | SQLAlchemy, pymysql, psycopg |  | Researching how to connect the API and extract the results from the favourites button into the Favoruties table and the reviews saved by the user into the reviews table. Some python libaries i researched which may be useful to create the connection: SQLAlchemy, pymysql, psycopg
17/05/2023 | API to DB connection | 1 hour 30 mins | NO | SQLAlchemy |  | Trying to make the connection using the SQLAlchemy library. No errors showing within code, however the data is still not showing in the tables. No progress made
18/05/2023 | API to DB connection | 45 mins | NO |  |  | Discussed with the group in class where I am up to with the connection. Have set a deadline for Sunday 21/05/2023 for the connection to be complete and running so then I can focus on unittesting next week. Not much progress made as still catching up on work while I was away and had to complete week 3 homework.
19/05//2023 | API to DB connection | 2 hours | NO | psycopg2 |  | Had 30 min call with Grace to discuss the task and any ideas she may have to complete the connection. Decided we would both look at the python libraries that can be used for mySQL connection. After the call carried on working on trying to establish the connection. This time using the psycopg2 library function. Still no progress made.
20/05/2023 AM | API to DB connection | 1 hour 30 mins | NO |  |  | Starting to feel abit lost now, tried lots of different solutions and still not getting any further. Have expressed feelings to rest of the group to see if they can also suggest any ideas. Feeling the pressure as I don't want to let the team down knowing the deadline for the successful connection should be ideally completed by tomorrow 21/05/2023.
20/05/2023 PM | API to DB connection | 2 hours | YES |  |  | Kath helped me complete the code to make the connection and managed to do it successfully and walked me through her code to change the tables to match the codes in the SQL database. Next step, working on the user id to be placed into the tables from the log in page that Mungu is working on.
21/05/2023 | Fetching the user id from the users table to extract it into the reviews and favourites table | 2 hours | NO |  |  | while trying to get the user id in the reviews and favourites tables, muddled up the code and lost the connection. Trying to fix the code to how it was before
22/05/2023 | Fetching the user id from the users table to extract it into the reviews and favourites table | 2 hours 30 mins | NO |  |  | meeting after class with group, Kath helped to debug my code again after losing the connection. Managed to save the information into the reviews table but getting an error to say that the favourites table doesnt exist. Discussed the project document with the group, assigned different parts of document to people but if any idea to add to any section.
23/05/2023 | User_id implementation | 40 mins | YES | pymysql |  | fixed code so that the favourites save in the table. Call with Kath to discuss how she made the user_id connection and went through the code line by line. Had to make a few tweaks so that it matched my table. Decided I prefered the semifinal.py version of the code which is a different layout for the page.
23//05/2023 | Project document | 30 mins | IN PROGRESS |  |  | Started working on the project document
23/05/2023 | Unit test | 45 mins | IN PROGRESS | unittest, mysql.connector, datetime, moc, patch, MagicMock |  | Working on unittest for the semifinal.py version. Have successfully got 2 tests passing for valid cases. Still need to work on invalid and edge cases.
24/05/2023 | Meeting with group | 30 mins | YES |  |  | Quick catch up with group after class to update where we are to and next steps
24/05/2023 | Unit test | 2 hours 30 mins | IN PROGRESS | unittest, mysql.connector, datetime, moc, patch, MagicMock |  | Changed unit tests for valid test cases as I realised although they were passing they were incorrect. Added unit test for invalid cases Now have 2 tests that pass successfully for valid and invalid add_data_to_db function. 2 tests failing for valid and invalid cases for save_review_rating_to_db function. Getting same error that the table reviews doesn't exist in the database and also an error for the add_data_to_db function because I had a different error when trying to insert a row but it already existed from another test.
25/05/2023 | Unit test | 2 hours | IN PROGRESS | unittest, mysql.connector, datetime, moc, patch, MagicMoc |  | Focusing on the unit test to try and complete. Still only 2 u tests passing now for valid and invalid add_data_to _db function. Created a function within the unit test to clean the tables to drop the tables when running each test to get rid of the error where the row already existed from a different test. This works for the add_data_to_db function, however still having the same issue for the save_review_rating_to_db functions for both valid and invalid cases where the error shows restaurant_app.reviews table doesn't exist. Started tests for the new functions.
26/05/2023 | Project diary | 30 mins | YES |  |  | Updated the correct layout for the project diary
26/05/2023 | Unit test | 3 hours 30 mins | IN PROGRESS | unittest, mysql.connector, datetime, moc, patch, MagicMock |  | Still only 2 tests successfully running. Removed the clean_tables function from the save_review_rating_to_db valid and invalid functions. Test will pass successfully the first time but when trying to run again it will fail due to the time stamp being different and the expected and actual result being different. Unsure of how to fix, asked group for ideas as deadline is nearing. Struggling to write unit tests for the 2 new functions display_restaurant and display_review_rating as unsure of which part of the function should be tested.
27/05/2023 | Unit test | 2 hours 30 mins | IN PROGRESS | unittest, mysql.connector, datetime, moc, patch, MagicMock |  | Still working on the above errors
27/05/2023 | Call with Fed | 20 mins | YES |  |  | Fed offering some help with the unit test, she created the test_create_connection function which worked in my computer to then try to add to the rest of the unittests I had created.
27/05/2023 | Unit test | 2 hours | IN PROGRESS | unittest, mysql.connector, datetime, moc, patch, MagicMoc |  | Working on the unit test with the bit of code that Fed did, added the rest of the tests that I had created. All tests still failing.
27/05/2023 | Call with group | 45 mins | YES | unittest, mysql.connector, datetime, moc, patch, MagicMock |  | Updating group on final things that need to be completed ready for submittting. Assigned final tasks, Fed offering to help some more with the unittest when she has time.
27/05/2023 | Unit test | 4 hours | IN PROGRESS |  |  | Decided to remove the display_restaurants and display_review_ratings functions from the unit test because they are not core functions of the class, so that I can focus on passing the tests for the core functions. For the add_data_to_db function which was passed yesterday is now failing because of 'None type object is not subscriptable. This is because the data is now not in the table, possibly because of the clean tables function I had created previously. I removed that bit of code but still got the same error, for some reason, the data won't save or add to the tables which is why the error is showing. For the save_review_rating_to_db_function I am struggling to mock and patch the datetime as it was failing due to the time being different each time the resr runs.
28/05/2023 | Unit test | 6 hours | YES | unittest, mysql.connector, datetime, moc, patch, MagicMock |  | Two tests successfully passing for valid and invalid cases for add_data_to_db function. Still failing for the save_review_rating_to_db, have worked on it continuously and still no progress. Getting a different error every time I change something. Kath tried to fix and also still failing, function was removed from testing as we do not have enough time to fix the error.
28/05/2023 | Project documentation | 2 hours 30 mins | YES |  |  | Added final pieces missing from the project document, made final changes and proof read document.
28/05/2023 | Final meeting with team | 1 hour | YES |  |  | Discussion with team for final finishing touches to the project and documentation before submitting.

## Fed
Federica Cimino
Date | Activity/Task | Time spent on Activity: | DONE | IN PROGRESS | HELP | Libraries Used | Links used | Reflection
SPRINT 1: WEEK 1
30.04.2023
| working on API | 30 min | trying to figure out wich API is best to use for restaurant finder trying Zomato an yelp
01.05.23 | trying to find out how to use Geolocation in order to have user to share their location and find restaurants | 1hr | code only works when entering a specific location
doent capture user location, updating code to Github
03/04.05 | working on input user, | 1hr | completed
05.05.23 | writing main code using api yelp user_location.py | 2 hrs | completed code where user is able to input location cuisine etc passed it to Kathleen to complete it with streamlit
08.05.23 | working on Refactoring codevvv | 1 hr | no progress yet
2023-09-05 | working on Refactoring code | 1 hr | Complete! Used list comprehension and set comprehension to simplify code Changed the message printed after adding restaurants to the database to include the number of restaurants added Removed the unnecessary if len(favorite_restaurants) > 0 check, since the loop will not execute if the list is empty.""" updated file on github
2023-10-05 | refactoring completed |  | divided main function in 4 smaller and more understandable function
2023-10-05 | starting working on exception handling | 30 mins | first function is done
2023-12-05 | working on exception handling | 1hr | trying to handle exception on when user enters incorrect input, still not working as i would like
14/05 | working on exception handling | 1hr | the code is written, not sure why is not printing the error when incorrect input are entered.
16/05 | exception handling | 30 mins | completed
17/05 | converting main code to Classes | 2 hrs | code tested seems working fine. Completed
19/05
22/05 | meeting catch up with the team | 30min | discussed about deadline and documentation
22/05 | working on documentation | 1 hr
23/05 | fixing some error handling messages | 1 hr | completed
24/05 | working on documentation | 30 min | completed
25.05 | worked on unittest for api | 1 hr | completed
27.05 | error handling on api fxing | 1 hr | completed, looks like now it s running the correct errors
27.05 | helped Nia with unittest | 30 mins | first unittest passed the other two still not passing
28.05 | helped Nia with unittest | 1 hr | managed to fix the unittest that test when data is added to database

## Grace
Grace Adeleke
Date | Activity/Task | Time spent on Activity: | DONE | IN PROGRESS | HELP | Libraries Used | Links used | Reflection
SPRINT 1: WEEK 1
31/04/23